Terms of Reference

Mobile Outreach Events to raise community awareness about NCDs and their prevention

Background

The Health for All Project in Albania (HAP) is funded by Swiss Agency for Development and Cooperation (SDC) of the Swiss Government and is being implemented by HAP Centre. Its overall goal is that the Albanian population benefit from better health due to improved Primary Health Care (PHC) services and health promotion activities.

In this framework, HAP will support mobile community health promotion events to raise awareness of the causes of non-communicable disease (NCDs) and their prevention.

The targeted area from the intervention is the Administrative Unit of Aranitas in the Municipality of Mallakaster and the Administrative Unit of Portez in the Municipality of Fier. The estimated number of residents in these areas is 15.000.

HAP is calling for a Non for Profit Organizations (NPO) with a strong record in community outreach to implement mobile outreach events according to the definitions in this TOR.

Objective

To implement innovative mobile outreach events designed by HAP to raise community awareness of the causes of non-communicable diseases (NCDs) and their prevention.

Specific objectives:

- To strengthen the health literacy of the community members regarding NCDs, empowering them to prevent chronic and degenerative illness by reducing risk factors, changing behaviors, and increasing demand for screening and treatment at the Health Centers.

- To engage and strengthen the Health Centres to lead and support communities in reducing their NCD-related risks.

Methods, Approaches, Deliverables

- The method and all the materials necessary for implementing the mobile outreach activities (implementing partner manual, IEC materials, training program, etc) have been developed by HAP.

- The mobile outreach activities will visit communities in the selected geographical areas, to address multiple NCD issues in a single event. The method enables substantial groups of people to circulate around 5 interactive, thematic stations (1-Introduction to the NCD risk factors, 2-Dietary risk and prevention, 3-Tabacco smoke exposure, 4-Alcohol consumption, 5-Inadequate physical activity). Two facilitators in each station will follow a script and use tools such as poster, games, quizzes to work with waves of groups of 10+/- people interactively for 15-20 minutes. Additionally, there will be 2 others stations. One where the entertaining facilitators will interact with younger children of the participating families and communities about healthy lifestyles and the other one where the local Health Centre staff, will answer  to participants questions and book cases on site for follow-up in the Health Centre.

- During the mobile outreach events, the implementing partner staff will implement the guides developed and provided by HAP. Related staff that will implement the activities will be trained by HAP on the innovative method and materials. Any healthcare and health prevention related questions formulated by community participants that are not covered in the guide provided by HAP must be directed to the Health Centre staff present in the event and should not be answered by the facilitators.

- HAP will liaise with the Health Centres of the communities to be visited in time to ensure that at least 2 Health Centre staff are present for each event and that the Health Centre staff are fully briefed on their roles (answering community questions, supporting the “NCD self-risk assessment”, and ensuring that participants with health concerns register for a follow-up appointment.

- The NPO will liaise in a timely manner with local authorities, community leaders, religious leaders, schools and relevant civil society and interest groups (e.g. disability, health groups and Roma organisations) to ensure their advanced information of the events in order that they can mobilise the community to attend forthcoming events.

- The NPO will be supervised by HAP. It will be supported technically, but the implementing partner will solve any issues related to transport, staffing etc. by itself.

- Budgeting of the activities should take into account the settings of implementation, targeted groups/community members, responsible actors/persons, time lines, required items and how they are going to be supervised and monitored. The budget proposal should be prepared using the template in Annex 1.

Based on the objectives of the Mobile Outreach Events, the expected deliverables are:

- 8 events implemented  (approximately 100 minutes each)

- 70 to 100 community members participate and benefit from each event (the activities will target whole communities and families and reach the primary target population of teenagers, young people and parents).

- A summary report on each event, with the number of beneficiaries by gender

Staff profile and duties

This section describes the characteristics of the team positions that NPO will need to mobilize and deploy. The team will have:

- A team leader/supervisor

- Thematic facilitators

- Entertaining facilitators

The team leader/supervisor – profile, tasks and skills:

- Should be mature, with not less than 10 years of experience in leading similar projects, activities or events

- Should have the problem-solving capacity to ensure that the mobile unit arrives, sets-up and commences, according to a plan of work agreed with HAP.

- He/she is responsible for quality assurance overall and that staff show high standard performance while implementing the mobile outreach events according to their guidance and training from HAP.

- Should have excellent logistical and planning skills to anticipate and/or deal with any issues arising to ensure smooth and efficient function of the events.

- He/she will be responsible for ensuring the accurate collection of required monitoring data and timely reporting.

- He/she will liaise with the Health Centres of the communities to be visited in time to ensure that at least 2 Health Centre staff are present for each event and that the Health Centre staff are fully briefed on their roles (answering community questions, supporting the “NCD self-risk assessment”, taking blood pressure and ensuring that participants with health concerns register for a follow-up appointment).

- He/she will also liaise in a timely manner with community leaders, religious leaders, schools and relevant civil society and interest groups (e.g. disability health groups and Roma organisations) to ensure their advanced information of the events in order that they can mobilise the community to attend forthcoming events.

The thematic station facilitators - profile and skills:

There will be 10 facilitators for five thematic stations.

- The team will have males and females in equal numbers.

- It is preferable to have facilitators with a background on health, social sciences or communication field.

- The facilitators will be trained by HAP on the messages to be conveyed to the target groups and they should be able to assimilate the materials, methods and training provided on NCDs and consistently implements the events in line with the guidelines.

- The facilitators should have the personality to faithfully implement the events according to training and guidance, to be bold communicators, team-players, and have charisma to engage communities with their enthusiasm

The entertaining facilitators - profile and skills:

There will be 5 entertaining facilitators to occupy and entertain children, incorporating health messages.

- At least 2 of them should have experience in entertaining and providing scripted health messages to children.

- At least 2 of them might have both theatrical and juggling skills

- Their role will include guiding participants to stations to maintain the flow of people participating in the event - these skills and experiences are important for the success of the event.

It is expected that NPO has 5 additional facilitators to ensure that they can always provide a full trained team, regardless of absence and illness.

Requirements for the offers and criteria for short listing the proposals:

The bidders for this contract should submit to the HAP Centre the following documents:

- The professional CV of the Organization demonstrating previous experiences in health promotion activities; communication, animation and facilitation of public events with the purpose of disseminating educative information and community mobilization;

- CV of the team leader

- Short bios (max half page) of each thematic and entertaining facilitators;

- A technical proposal of not less than 3 pages describing in detail how the bidder will:

- Organize the space of the previously mentioned thematic and entertaining stations in the assigned area;

-Entertain children too young to engage in the tobacco and alcohol stations, and provide age-appropriate preventive information (e.g. with games, puppet shows, video kiosks)

-Ensure that waves of participants move in a flow to stations and prevent bottlenecks (describe techniques and or tools to be used to ensure the movement of people)

-Encourage all family groups to visit all stations, including the sixth HC station (describe techniques and/or incentives to be used)

-Organise the ideas for the healthy snacks offered at the end of the event, as this is an important learning opportunity for communities (proposed receipts aiming especially to grab the attention of the kids and their parents; how will the snacks be served; how will the transport be managed in order to provide fresh and safe food)

-Organizational aspects related to permission from local authorities/police etc., use of public space for the event, agreements related to cleaning of the territory at the end of the event and other organization and logistic issues.

- Budgeted plan of activities as described in Annex 1

Deliverables and contractual aspects

For the implementation of the contract, the provider will work in close collaboration with and under supervision of HAP Fier coordinator and HAP Health Promotion Officer. HAP Fier coordinator and HAP Health Promotion Officer will assure that the provider will perform the activities as planned and in line with the contract.

The deliverables of the contract will be:

- Narrative Report on activities carried in line with the implementation plan for each event. The report should conclude with lessons learned and recommendations for future implementation of the Mobile Outreach Activities.

Time Frame

The Implementation of the activities of the plan should take place starting from 12 March 2018 to 12 April 2018. The first two events should take place in Portez Administrative Unit (Fier).

Deadline for application

Offers should be submitted in electronic version, labeled: “Mobile Outreach Events to raise community awareness about NCDs and their prevention” within 20th February 2018, 4 pm to the e-mail address: info@hap.org.al .